## BURNDOWN CHARTS
SPRINT 1
Issue # | User Story | Description | Associated Tasks | Assigned Member | Story Points (0.5,1,2,3,5,8,13) | Priority | Risk | Due Date
1 | User can access the home page of the website and navigate to different pages | - Home page of the website - It should contain the page's name and logo - Offer login an signup button to navigate to their respective pages - Add links to other pages such as: about us, features, others - Add a description of the system on the home page | Create a mockup for the home page | Dara | 3 | Medium | Low Home page is needed for all the other tabs to be accessible and it does not depend on other tasks. Furtheremore, the creation of it does not require a lot of technical knolwedge and challenges. | 2024-09-29
|  |  | Code the frontend based on the mockup | Oren |  |  |  | 2024-09-29
|  |  | Create the navigation routes between different pages | Oren |  |  |  | 2024-09-29
2 | User can create an account | - Page for user account creation - It will require the user to enter their information (name ,last name , user type, password, email, etc) - The information will be submitted and saved in the backend server | Create a mockup for the account creation page | Dara | 8 | High | Low Users have to create account in order to use the website features. It is a needed requirement and does not depend on other tasks and features. | 2024-09-29
|  |  | Code the backend API routes for account creation | Daniel |  |  |  | 2024-09-29
|  |  | Create student and teacher migrations for MySQL database | Daniel |  |  |  | 2024-09-29
Mathieu
|  |  | Code the backend API routes for logging in | Daniel |  |  |  | 2024-09-29
|  |  | Setup Flask backend with Docker | Daniel |  |  |  | 2024-09-29
|  |  | Setup ReactJS frontend with Docker | Daniel |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Mathieu |  |  |  | 2024-09-29
|  |  | Code the frontend (name, email, password, confirm password, user type fields) | Oren |  |  |  | 2024-09-29
3 | User should be able to login | - Page for the user to login using their credentials - Links can be given to reset password and navigating back to the sign up page | Create a mockup for the user login page | Dara | 5 | High | Medium Users need to log in after they created their account, otherwise they cannot use the website, therefore a really important feature. However, it needs the account creation to be done, especially backend wise. | 2024-09-29
|  |  | Code the backend API routes for logging in | Daniel |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Mathieu |  |  |  | 2024-09-29
|  |  | Code the frontend based on the mockup | Brandon |  |  |  | 2024-09-29
|  |  | Add links to password reset and sign up page | Brandon |  |  |  | 2024-09-29
4 | Instructor should be able to create teams once logged in | - Once logged in, they have access to a button to create teams. - Instructors have access to all the students in the databse to create the teams - They can select students and create a team for them. - Once a team is created, it should be visible in the instructor's home page | Create a mockup of the team creation page | Dara | 8 | High | Medium The server needs to be populated with students for the instructor to be able to create the teams. Team creation might need some knowledge that the team does not already require, meaning research is needed. | 2024-09-29
|  |  | Code the frontend (create teams button, selecting students checkboxes, finalize team creation button, teams preview in the home page) | Marc |  |  |  | 2024-09-29
|  |  | Code the backend (API calls, previewing the student names,etc) | Daniel |  |  |  | 2024-09-29
5 | Instructor can export the list of students as a csv file | - After accessing the team creation page, the teacher should have the option to download a csv file containing the list of all students | Implement csv exporting functionality in the frontend | Marc | 5 | Medium | High Including the export csv functinality can be time consuming due to lack of knowledge of the team on this topic. Research is needed. | 2024-09-29
|  |  | code the necessary backend API routes to retrieve the list of students | Mathieu |  |  |  | 2024-09-29
6 | Users can see the teams created | - Create a "TEAMS" tab where all the teams are listed and can be visualized | Create mockup for the teams tab and how the teams are listed | Dara | 3 | High | Medium Depends on other tasks to be implemented before (team creation). | 2024-09-29
|  |  | Code the frontend based on the mockup provided | Oren |  |  |  | 2024-09-29
|  |  | Code the backend routes | Daniel |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Dara |  |  |  | 2024-09-29
SPRINT 2
Issue # |  | User Story Title/Task Title | Description/Associated Tasks | Assigned Member | Story Points (0.5,1,2,3,5,8,13) | Priority | Risk | Due Date
1 | User can reset their password |  | -Draw a mockup for the user reset password -Implement the mockup on React/HTML -Define fields constraints and requirements -Ensure all fields follow requirements |  |  | Low
User can contact the team members via email
Student should get notified once they are added in a team
SPRINT 3
Issue # |  | User Story Title/Task Title | Description/Associated Tasks | Assigned Member | Story Points (0.5,1,2,3,5,8,13) | Priority | Risk | Due Date
Low