## BURNDOWN CHARTS
SPRINT 1
Issue # | User Story | Description | Associated Tasks | Assigned Member | Story Points (0.5,1,2,3,5,8,13) | Priority | Risk | Due Date
1 | User can access the home page of the website and navigate to different pages | - Home page of the website - It should contain the page's name and logo - Offer login an signup button to navigate to their respective pages - Add links to other pages such as: about us, features, others - Add a description of the system on the home page | Create a mockup for the home page | Dara | 3 | Medium | Low Home page is needed for all the other tabs to be accessible and it does not depend on other tasks. Furtheremore, the creation of it does not require a lot of technical knolwedge and challenges. | 2024-09-29
|  |  | Code the frontend based on the mockup | Oren |  |  |  | 2024-09-29
|  |  | Create the navigation routes between different pages | Oren |  |  |  | 2024-09-29
2 | User can create an account | - Page for user account creation - It will require the user to enter their information (name ,last name , user type, password, email, etc) - The information will be submitted and saved in the backend server | Create a mockup for the account creation page | Dara | 8 | High | Low Users have to create account in order to use the website features. It is a needed requirement and does not depend on other tasks and features. | 2024-09-29
|  |  | Code the backend API routes for account creation | Daniel |  |  |  | 2024-09-29
|  |  | Create student and teacher migrations for MySQL database | Daniel |  |  |  | 2024-09-29
Mathieu
|  |  | Code the backend API routes for logging in | Daniel |  |  |  | 2024-09-29
|  |  | Setup Flask backend with Docker | Daniel |  |  |  | 2024-09-29
|  |  | Setup ReactJS frontend with Docker | Daniel |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Mathieu |  |  |  | 2024-09-29
|  |  | Code the frontend (name, email, password, confirm password, user type fields) | Oren |  |  |  | 2024-09-29
3 | User should be able to login | - Page for the user to login using their credentials - Links can be given to reset password and navigating back to the sign up page | Create a mockup for the user login page | Dara | 5 | High | Medium Users need to log in after they created their account, otherwise they cannot use the website, therefore a really important feature. However, it needs the account creation to be done, especially backend wise. | 2024-09-29
|  |  | Code the backend API routes for logging in | Daniel |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Mathieu |  |  |  | 2024-09-29
|  |  | Code the frontend based on the mockup | Brandon |  |  |  | 2024-09-29
|  |  | Add links to password reset and sign up page | Brandon |  |  |  | 2024-09-29
SPRINT 2
Issue # |  | User Story Title/Task Title | Description/Associated Tasks | Assigned Member | Story Points (0.5,1,2,3,5,8,13) | Priority | Risk | Due Date
4 | As an instructor, I want to be able to create teams of students so that I can manage their workflow in the peer assessment system | - Once logged in, they have access to a button to create teams. - Instructors have access to all the students in the databse to create the teams - They can select students from the list and create a team for them. - Access Mockup here! | Create a mockup of the team creation page | Dara | 5 | High | Medium The server needs to be populated with students for the instructor to be able to create the teams. Team creation might need some knowledge that the team does not already require, meaning research is needed. | 2024-09-29
|  |  | Code the frontend (create teams button, selecting students checkboxes, finalize team creation button, teams preview in the home page) | Marc |  |  |  | 2024-09-29
|  |  | Code the backend (API calls, previewing the student names,etc) | Daniel, Mathieu |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Dara
5 | As an instructor, I want to visualize the teams created so that I can access them and modify them if needed | - After successful login, the instructor has access to all the teams and can visualize them - The teams will be listed one by one while displaying the information of the students that are part of them. - Access Mockup here! | Create a mockup for the instructor's team visualization | Dara | 5 | High | Medium Depends on other tasks to be implemented before (team creation). | 2024-09-29
|  |  | Code the frontend based on the mockup provided | Marc |  |  |  | 2024-09-29
|  |  | Code the backend | Daniel, Mathieu |  |  |  | 2024-09-29
|  |  | Establish the frontend-to-backend connection | Marc |  |  |  | 2024-09-29
6 | As a student, I want to visualize my team so that I can access it and evaluate my peers | - After successful login, the student should be able to see their respective team if they have been put in a team by the instructor. - If the instructor makes a team with that student while the student is already logged in, refreshing the page should display the team. - The displayed component should contain the team's name and the list of students being part of it. - Access Mockup here! | Create a mockup for the student's team visualization | Dara | 8 | High | Medium Depends on other tasks to be implemented before (team creation) | 2024-10-27
|  |  | Code the frontend based on the mockup design | Oren |  |  |  | 2024-10-27
|  |  | Code the backend (API calls, database modifications) | Mathieu, Daniel |  |  |  | 2024-10-27
|  |  | Establish the frontend-to-backend connection | Oren |  |  |  | 2024-10-27
7 | As an instructor, I want to be able to modify a team after it has been created so that I can change a team's formation | - Instructors should be able to modify a team after it has been created. - Provide a "Delete" and/or "Edit" button that allows the instructor to modify or remove a team that has been created - They should be able to remove or add students to a team and save the changes - The changes should be updated on both students and instructors team visualization pages - Access Mockup Here (Changes to Instructor Page, Team Deletion, Team Modification) | Create a mockup design for the team modificaiton feature | Dara | 2 | High | High This user story can pose siginifant challenges implementation wise since it requires a good knowledge of the backend and frontend interaction Has a high impact on other features if not implemented well Depends on other activities (team creation) | 2024-10-27
|  |  | Code the frontend based on the new mockup design | Brandon |  |  |  | 2024-10-27
|  |  | Code the backend (additional routes) | Daniel, Mathieu |  |  |  | 2024-10-27
|  |  | Establish the frontend-to-backend connection | Oren |  |  |  | 2024-10-27
8 | As a student, I want to be able to select a teammate from my team so that I can evaluate their performance anonymously | - Students have access to a "evaluate" button which redirects them to the evaluation page where they can choose a specific teammate and start assessing their performance - Students cannot choose multiple teammates at the same time - The list of teammates only displays those for whom the evaluation has not been submitted - Access Mockup here! | Create a mockup for teammate selection for evaluation | Dara | 3 | High | Medium Not too complex to implement Depends on other features to be implemented first (team creation) | 2024-10-27
|  |  | Code the frontend | Brandon |  |  |  | 2024-10-27
|  |  | Code the backend | Daniel, Mathieu |  |  |  | 2024-10-27
|  |  | Establish the frontend-to-backend connection | Oren |  |  |  | 2024-10-27
9 | As a student, I want to be able to evaluate a selected teammate based on the Cooperation dimension so that I can provide feedback | - After selecting a teammate, the student is redirected to the evluation form/page where they can evaluate their teammate based on different categories. - The form will only contain the cooperation section for now. - Various cooperation actions and criteria should be brainstormed and selected to optimally evaluate the teammates' performance on this dimension - The student will evaluate their teammate on a 5-point scale for each of the "cooperation" criteria/components and the average rounded to the closest integer will be the teammate's cooperation score (out of 5) - Once the form completed (all entries required), the student can confirm their evaluation submission. - After successful submission, the teammate's name should be removed from the selection list in the evaluation page - Access Mockup Here! | Brainstorm coopperation criteria/elements that the student can be evaluted on | Brandon, Oren | 3 | High | High Also depends on other features to be implemented first (team cration and teammate selection) Might be heavy/complex implementation wise | 2024-10-27
|  |  | Create a mockup for the evaluation page/form | Dara |  |  |  | 2024-10-27
|  |  | Code the frontend (evaluation page) | Marc |  |  |  | 2024-10-27
|  |  | Code the backend (probably one single route to store the average cooperation value for the chosen teammate) | Daniel, Mathieu |  |  |  | 2024-10-27
|  |  | Establish the frontend-to-backend connection | Marc |  |  |  | 2024-10-27
10 | As an instructor, I want to be able to visualize the score of each student based on the evaluation dimensions so that I can quickly assess their productivity and contribution to the team | - Modify the team visualization for the instructor by adding the dimension fields for each team. - That way, each student's score for each dimension will be shown and updated as the students evaluate them throughout the semester - Access Mockup Here! | Create a mockup for the evaluation dimension visualization | Dara | 3 | Medium | Medium Depends on a lot of features to be implemented before (team creation, teammate selection, teammate evaluation) Not too complex to develop | 2024-10-27
|  |  | Code the frontend based on the mockup | Brandon |  |  |  | 2024-10-27
|  |  | Code the backend | Daniel, Mathieu |  |  |  | 2024-10-27
|  |  | Establish the frontend-to-backend connection | Oren |  |  |  | 2024-10-27
11 | As a student, I want to be able to evaluate a selected teammate based on the Conceptual Contribution dimension so that I can provide feedback | - Extend the evalutation page by adding the "Conceptual Contribution" questions and evaluation criteria | Create the corresponding mockup | Dara | 2 | Low | Medium Depends on a lot of features to be implemented before (team creation, teammate selection, teammate evaluation) Not too complex to develop | TBD
|  |  | Code the frontend based on the mockup | Oren |  |  |  | TBD
|  |  | Code the backend | Daniel |  |  |  | TBD
|  |  | Establish the frontend-to-backend connection | Marc |  |  |  | TBD
12 | As a student, I want to be able to evaluate a selected teammate based on the Practical Contribution dimension so that I can provide feedback | - Extend the evalutation page by adding the "Practical Contribution" questions and evaluation criteria | Create the corresponding mockup | Dara | 2 | Low | Medium Depends on a lot of features to be implemented before (team creation, teammate selection, teammate evaluation) Not too complex to develop | TBD
|  |  | Code the frontend based on the mockup | Dara |  |  |  | TBD
|  |  | Code the backend | Mathieu |  |  |  | TBD
|  |  | Establish the frontend-to-backend connection | Brandon |  |  |  | TBD
13 | As a student, I want to be able to evaluate a selected teammate based on the Work Ethic dimension so that I can provide feedback | - Extend the evalutation page by adding the "Work Ethic" questions and evaluation criteria | Create the corresponding mockup | Dara | 2 | Low | Medium Depends on a lot of features to be implemented before (team creation, teammate selection, teammate evaluation) Not too complex to develop | TBD
|  |  | Code the frontend based on the mockup | Daniel |  |  |  | TBD
|  |  | Code the backend | Brandon |  |  |  | TBD
|  |  | Establish the frontend-to-backend connection | Oren |  |  |  | TBD
14 | As a stduent, I want to be able to write additional comments about the performance of my peers so that I can go further in my analysis if needed | - This can be implemented by adding message boxes at the end of the evaluation form so that the evaluator can write additional comments if they desire to. - The message should be encrypted and be sent to the backend , so that it can be retrieved later on to be displayed for the instructor. | Create the corresponding mockup | Dara | 3 | Low | Medium Depends on a lot of features to be implemented before (team creation, teammate selection, teammate evaluation) Not too complex to develop | TBD
|  |  | Code the frontend based on the mockup | Marc |  |  |  | TBD
|  |  | Code the backend | Mathieu |  |  |  | TBD
|  |  | Establish the frontend-to-backend connection | Oren |  |  |  | TBD
X | As a student, I want to be able to modify my evaluation for a certain teammate after I have submitted it so that I can change my assessement
X | As a user, I want to be able to logout from the system so that I can close my session
X | Instructor can export the list of students as a csv file | - After accessing the team creation page, the teacher should have the option to download a csv file containing the list of all students | Implement csv exporting functionality in the frontend | Marc | 5 | Medium | High Including the export csv functinality can be time consuming due to lack of knowledge of the team on this topic. Research is needed. | 2024-09-29
|  |  | code the necessary backend API routes to retrieve the list of students | Mathieu |  |  |  | 2024-09-29
X | User can reset their password |  | -Draw a mockup for the user reset password -Implement the mockup on React/HTML -Define fields constraints and requirements -Ensure all fields follow requirements |  |  | Low
X | User can contact the team members via email
X | Student should get notified once they are added in a team
SPRINT 3
Issue # |  | User Story Title/Task Title | Description/Associated Tasks | Assigned Member | Story Points (0.5,1,2,3,5,8,13) | Priority | Risk | Due Date
Low
ACCEPTANCE TESTS
Issue # | Name & Description
3 | User Login 1. User presses on the "Login" button located on the website's home page. 2. User is navigated to the "Login" page. 3. User enters their credentials (Email address & Password) a. If the user enters an invalid email address, a pop-up message indicates the correct format required. 4. User pressess the "Log In" button. a. If the user entered wrong credentials, pressing the button will display a RED message indiating the reason of unsuccessful log in. 5. User is taken to the home page upon successful Log In.
4 | Instructor Team Creation 1. User (Instructor) presses on the "Create a New Team" button 2. User is taken to the team creation page 3. User chooses a "Team Name" and selects the team members from the list displayed a. The list of students displays all the students that are not yet in a team. 4. User presses on the "Confirm" button. a. If a team with a similar name already exists, a RED text message indicates the latter so the user can change the name chosen. b. If the user presses the "Cancel" button, they are taken back to their home page 5. The user is navigated to their home page and can now visualize the team just created at the top of the teams' list.
8 | Selecting a Team Member for Evaluation 1. User (Student) presses "Evaluate a Team Member" button 2. User is taken to the teammate selection page a. The selection page dipslays the names of the teammates who have not yet been evaluated. 3. User selects a team member of their team by checking the corresponding checbox a. User cannot select multiple team members at once, selecting another team member removes the previous selection. 4. User presses on the "Start Evaluation" button a. If the user selects the "Cancel" button, they go back to their home page. 5. User is redirected to the evaluation page to start evaluating the chosen team member.